## Project Summary
CASE TYPE BACKLOG TOOL
Release Date: | 2023-01-01 | Tool Version: | v-39 | © 2023 Pegasystems, Inc. All rights reserved.
CLIENT / ENGAGEMENT DATA
*Client Name: |  | GoGoRoad | * Engagement Name: |  | Automotive service
*Sizing Generated By: |  | ABC | *Sizing Verified By: |  | DEF
Created: |  | 2019-06-24 12:21 | Last Modified: |  | 2023-06-13 08:58
CHANGE LOG
2023-06-13 11:33 | Updates were made to the following tabs: Case Types
2023-06-13 09:09 | Updates were made to the following tabs: Interfaces, Personas, Case Types
2023-06-13 08:18 | Updates were made to the following tabs: Personas, Case Types, Supporting Features
2023-05-18 14:12 | Updates were made to the following tabs: Case Types
2023-05-18 10:18 | Updates were made to the following tabs: Project Attributes
2023-05-18 10:18 | Updates were made to the following tabs: Case Types, Supporting Features
2023-05-18 10:17 | Updates were made to the following tabs: Case Types, Supporting Features
2023-05-18 10:17 | Updates were made to the following tabs: Interfaces, Case Types
2023-05-18 10:16 | Updates were made to the following tabs: Project Attributes
2023-05-18 10:16 | Updates were made to the following tabs: Case Types, Supporting Features
2023-05-18 10:15 | Updates were made to the following tabs: Interfaces
2023-05-18 10:12 | Updates were made to the following tabs: Case Types, Supporting Features
2023-05-18 10:08 | Updates were made to the following tabs: Case Types, Supporting Features
2023-05-17 14:30 | Updates were made to the following tabs: Personas, Case Types, Reports
2023-05-17 14:22 | Updates were made to the following tabs: Personas, Case Types, Supporting Features
2023-05-17 13:16 | Updates were made to the following tabs: Case Types
2023-05-17 10:19 | Updates were made to the following tabs: Interfaces, Case Types, Supporting Features, Reports
2023-05-17 10:02 | Updates were made to the following tabs: Personas, Case Types, Supporting Features
2023-05-15 16:06 | Updates were made to the following tabs: Personas, Case Types
2023-05-15 15:58 | Updates were made to the following tabs: Case Types, Project Attributes
2023-05-15 14:37 | Updates were made to the following tabs: Case Types
2023-05-15 14:31 | Updates were made to the following tabs: Personas, Case Types
Dev Mode
Reset Macros

## Assumptions
ASSUMPTIONS
1 | SelfService portal is a future requirement. It is not in scope for MLP1.
2 | No data migration is involved.
3 | Minimal branding is required for this application.
4 | Email and sms notifications should be sent to customers during the case life cycle. Out-of-the-box triggers will be used. Templates will be defined during the project.
5 | The calculated cost of service does not impact the type or urgency of payment.
6 | Full membership application and membership renewal are not in scope for MLP1. Customers will need to provide payment method at the time of service request and be expected to pay upon invoicing.
7 | Out-of-the-box routing logic is included in scope for MLP1, and to be defined during the project life cycle.
8 | Out-of-the-box SLAs are included in project scope for MLP1, and to be defined during the project life cycle.
9 | Escalations for SLAs are to be included in project scope with MLP1, and to be defined during the project life cycle.
10 | Application should be developed to easily extend service capabilities
11 | For MLP1, service request can be iniated by webpage only. Mobile capabilities in scope for MLP2.
12 | For MLP1, the service provider will be selected manually by GoGoRoad CSR. This selection will take place outside of the application. Automatic selection based on location in scope for MLP2.
13 | Application solution does not include any BI extract of data for reporting.
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Microjourneys
2
Microjourneys
# | Microjourney | Description
0
1 | Membership application | Possibility to request membership for GoGoRoad
2 | Roadside assistance request | Possibility to request roadside assistance based on different circumstances
3 | Membership renewal | Possibility to renewal membership after defined period of time
Add Rows
Instructions
1. Enter all Microjourneys here

## Case Types
1
Case Types
# | Case Type | Parent Microjourney(s) (Multi-Select) | Average Complexity | Channels |  |  |  | Assumptions
|  |  |  | Call Center / Desktop | Mobile App | Web Self Service | Other
0 |  |  | <Select> | 100% | 0% | 0% | 0%
1 | Membership Application | Membership application | Low | 75% | 25% | 0% | 0% | Membership application takes place via call a Call center desktop portal (MLP1) and mobile app (MLP2)
2 | Assistance Request | Roadside assistance request | Medium | 25% | 50% | 25% | 0% | An Assistance Request takes place via call a Call center desktop portal (MLP1) and mobile app (MLP2)
3 | Membership Renewal | Membership renewal | Medium | 25% | 50% | 25% | 0% | Membership application takes place via a user portal and mobile app (MLP2)
4 | Service | Roadside assistance request | Medium | 50% | 50% | 0% | 0% | Subcase for roadside assistance. Organize and invoice services related to the Assistance Request.
Add Rows
Instructions
1. Enter all Case Types here
2. Refer to contextual help by hovering over column heading
Note on D4: Low - Up to 3 stages, 10 steps total Medium - 4- 6 stages, 20 steps total High - 7 -9 stages, 30 steps total Complex - 10+ stages. Note: this is probably too big and should be split into two or more Case Types
Note on E4: What channels will this case type be built for? Form allows for 25% increments for patial channel exposure. Total may be greater than 100% as a case type can be built for multiple channels.
Note on H5: For Example" PegaPulse, service driven headless, etc.

## Supporting Features
1
Supporting Features
# | Feature | Which Case Types is this Feature in support of? (Multi-Select) | Average Complexity | Channels |  |  |  | Assumptions
|  |  |  | Call Center / Desktop | Mobile App | Web Self Service | Other
0 |  |  | <Select> | 100% | 0% | 0% | 0%
1 | Existing Authentication & Security | Assistance Request, Membership Application, Membership Renewal | OOTB | 50% | 50% | 0% | 0% | Utilize existing authentication and security configuration.
2 | Web Portals | Assistance Request, Service, Membership Application, Membership Renewal | Medium | 25% | 50% | 25% | 0% | Pega out-of-the-box portal developed for MLP1. Mobile in scope for MLP2.
3 | Request assistance | Roadside assistance request, Assistance Request | Medium | 25% | 50% | 25% | 0% | Manual request for service initiates an Assistance Request case
4 | Check customer status | Assistance Request | Low | 25% | 50% | 25% | 0% | Verify membership status of customer to determine if payment information is required (Gold status = no payment information required)
5 | Manage payment | Roadside assistance request, Assistance Request | High | 25% | 50% | 25% | 0% | Guarantee payment by requiring credit card information
6 | Identify customer | Roadside assistance request, Assistance Request | Low | 25% | 50% | 25% | 0% | Select customer from dropdown list
7 | Identify automotive issue | Assistance Request | Low | 25% | 50% | 25% | 0% | Select automotive issue from the predefined list
8 | Enter location Information | Assistance Request | Low | 25% | 50% | 50% | 0% | Identify service location on Google maps
9 | Enter vehicle Information | Assistance Request | Low | 25% | 50% | 50% | 0% | Input identifying information about the vehicle
10 | Enter payment Information | Assistance Request | Low | 25% | 50% | 50% | 0% | Input credit card information
11 | Verify membership and prompt enrollment | Assistance Request | Low | 25% | 50% | 50% | 0% | Automate process for confirming membership in GoGoRoad. If not a member, prompt for enrollment (MLP1). Full membership to be offered as part of MLP2.
12 | Select service provider | Assistance Request | Medium | 25% | 50% | 50% | 0% | System select provider based on the business conditions
13 | Initiate service call | Assistance Request | OOTB | 25% | 50% | 50% | 0% | System create a service case on proper stage of Roadside assistance
14 | Wait for completed service | Assistance Request | OOTB | 25% | 50% | 50% | 0% | System waits with the roadside assistance till service is done
15 | Review service information | Service | OOTB | 50% | 50% | 0% | 0% | Review selected activities during the service
16 | Invoice customer | Service | Low | 50% | 50% | 0% | 0% | Invoice customer based on the services performed
17 | Identify service(s) performed, quantity, unit price | Service | OOTB | 50% | 50% | 0% | 0% | Service provider has capability to identify services performed, quantity, unit price, and description for records
18 | Resolve Service case | Service | OOTB | 50% | 50% | 0% | 0% | System automatically resolves a Service case when service is complete and invoice has been issued.
19 | Membership application | Membership application | Low | 75% | 25% | 0% | 0% | Extend cutomer option for full membership to GoGoRoad services (MLP2)
20 | Membership renewal | Membership renewal | Medium | 25% | 50% | 50% | 0% | When membership period is close to expiration automatically issue option for renewal (MLP2)
21 | Exception path | Roadside assistance request | Low | 25% | 50% | 50% | 0% | Provide path for exception processing such as cancellation of the service request
22 | Duplicate Case check | Roadside assistance request | OOTB | 25% | 50% | 50% | 0% | Identify potential duplicate service request cases
Add Rows
Instructions
1. Enter all application-wide Supporting Features here
2. Refer to contextual help by hovering over column heading
Note on B4: A Supporting Feature is not a stage or step but rather an application wide feature that typically supports or enhances 1 or many case types
Note on C4: Multi-Select picklist to associate the feature with any case types that it supports Use Delete key to clear.
Note on D4: Low - Up to 5 days effort Medium - 5 - 10 days effort High - 11 - 15 days effort Complex - 16+ days effort. Note: this is probably too big and should be split into two or more Features
Note on E4: What channels will this feature be built for? Form allows for 25% increments for patial channel exposure. Total may be greater than 100% as a featurel can be built for multiple channels.
Note on H5: For Example" PegaPulse, service driven headless, etc.

## Interfaces
-1
Interfaces
# | Interface Name | Service or Connector | Interface / Data Source Type | Complexity | Interface Data Source Exists? | Assumptions
0 |  | <Select> | <Select> | <Select> | <Select>
1 | Members data | Connector | Connect REST | Medium | Yes | Support for POST and GET action, MODIFY do not supported
2 | Service providers | Connector | Connect SOAP | High | Yes | Get the list of all providers under provided address
3 | Payment | Connector | Connect SOAP | High | Yes | Managaing of the credit card payments
4 | Billing system | Connector | Connect SOAP | Medium | Yes | Sending payment and generating the invoice
5 | SMS server | Connector | Connect REST | Low | Yes | Sending of the SMS's
6 | Email Server | Connector | Connect REST | Low | Yes | Sending of the emails
7 |  | <Select> | <Select> | <Select> | <Select>
8 |  | <Select> | <Select> | <Select> | <Select>
9 |  | <Select> | <Select> | <Select> | <Select>
10
11
Add Rows
Instructions
1. Enter all interfaces here
2. Refer to contextual help by hovering over column heading
Note on C4: Is this a Service or a Connector? Service: External system initiates call to Pega app Connector: Pega app initiates call to external system
Note on D4: Select the interface or data source type. Use unknown if you don't know at this point
Note on E4: Low - Simple Data mapping only E.g. SOAP typically with a WSDL Medium - Interpretation of the data into Pega. Typically 20-50 fields High - Lots of data with complex meanings. Typically 50+ fields
Note on F4: Yes = Existing - the client has a system and interface that does this, so Pega work will be simple mapping (SOAP or similar) and we assume a WSDL or similar is available No = New - this needs to be built new by the client, so will be built in parallel to Pega and no WSDL or spec is available

## Personas
1
Personas
# | Personas | Assumptions
0
1 | Customer | Requesting automotive assistance, service, membership and membership renewal
2 | CSR | Call center operator managing the assitance request (MLP1), customer information, service dispatch, and payment
3 | Service provider | Providing service to the customer based on the request, detailing services provided
4 | Service manager | Verifying work of the service provider
Add Rows
Instructions
1. Enter all Personas/Roles here

## Reports
2
Reports & Correspondences
# | Report or Correspondence | Average Complexity | MLP Release | Assumptions
0 |  | <Select> | <Select>
1 | Cases requested | Low | MLP1 | A report to track the status of Assistance requests over the last 30 days
Add Rows
Instructions
1. Enter all Reports here
2. Refer to contextual help by hovering over column heading
Note on C4: Low - Straightforward display of data. No manipulation, calculations, etc Medium - Calculation or inferences required High - Reporting on data we don't have, calculations, inferences, and complex formatting required

## Work Backlog
Case Type Backlog
Work To Do | [5 empty] | Interfaces | [5 empty] | Personas |  |  |  | Channels |  |  |  | Biz Value | Release | Sizing Assumptions
# | C or F | Microjourney | Case Type/ Feature | Which case types is this feature in support of? | Average Complexity | Members data | Service providers | Payment | Billing system | SMS server | Email Server | Customer | CSR | Service provider | Service manager | Call Center / Desktop | Mobile App | Web Self Service | Other | L/M/H | MLP Release | Assumptions
0 |  |  |  |  | <Select> | [10 empty] | 0% | 0% | 0% | 0% | <Select> | <Select>
1 | C | Membership application | Membership Application | Membership application | Low | x |  | x | x | x | x | x | x |  |  | 75% | 25% | 0% | 0% | Medium | MLP2
2 | C | Roadside assistance request | Assistance Request |  | Medium | x | x | x | x | x | x | x | x |  |  | 25% | 50% | 25% | 0% | High | MLP1
3 | C | Membership renewal | Membership Renewal | Membership renewal | Medium | x |  | x | x | x | x | x | x |  |  | 25% | 50% | 25% | 0% | Medium | MLP2
4 | C | Roadside assistance request | Service |  | Medium | x |  |  |  | x | x |  |  | x | x | 50% | 50% | 0% | 0% | High | MLP1
5 | F |  | Existing Authentication & Security | Assistance Request, Membership Application, Membership Renewal | OOTB | [6 empty] | x | x | x | x | 50% | 50% | 0% | 0% | Medium | MLP1
6 | F |  | Web Portals | Assistance Request, Service, Membership Application, Membership Renewal | Medium | [6 empty] | x | x | x | x | 25% | 50% | 25% | 0% | Low | MLP2
7 | F |  | Request assistance | Roadside assistance request, Assistance Request | Medium | [6 empty] | x | x |  |  | 25% | 50% | 25% | 0% | High | MLP1
8 | F |  | Check customer status | Assistance Request | Low | [10 empty] | 25% | 50% | 25% | 0% | Medium | MLP2
9 | F |  | Manage payment | Roadside assistance request, Assistance Request | High | [10 empty] | 25% | 50% | 25% | 0% | High | MLP1
10 | F |  | Identify customer | Roadside assistance request, Assistance Request | Low | x | [5 empty] | x | x |  |  | 25% | 50% | 25% | 0% | Low | MLP1
11 | F |  | Identify automotive issue | Assistance Request | Low | [6 empty] | x | x |  |  | 25% | 50% | 25% | 0% | Medium | MLP1
12 | F |  | Enter location Information | Assistance Request | Low | [6 empty] | x | x |  |  | 25% | 50% | 50% | 0% | Low | MLP1
13 | F |  | Enter vehicle Information | Assistance Request | Low | [6 empty] | x | x |  |  | 25% | 50% | 50% | 0% | Low | MLP1
14 | F |  | Enter payment Information | Assistance Request | Low |  |  | x |  |  |  | x | x |  |  | 25% | 50% | 50% | 0% | Medium | MLP1
15 | F |  | Verify membership and prompt enrollment | Assistance Request | Low | [10 empty] | 25% | 50% | 50% | 0% | Medium | MLP2
16 | F |  | Select service provider | Assistance Request | Medium | [7 empty] | x |  |  | 25% | 50% | 50% | 0% | Low | MLP1
17 | F |  | Initiate service call | Assistance Request | OOTB | [10 empty] | 25% | 50% | 50% | 0% | Low | MLP1
18 | F |  | Wait for completed service | Assistance Request | OOTB | [10 empty] | 25% | 50% | 50% | 0% | Low | MLP1
19 | F |  | Review service information | Service | OOTB | [9 empty] | x | 50% | 50% | 0% | 0% | Low | MLP1
20 | F |  | Invoice customer | Service | Low | [9 empty] | x | 50% | 50% | 0% | 0% | High | <Select>
21 | F |  | Identify service(s) performed, quantity, unit price | Service | OOTB | [8 empty] | x |  | 50% | 50% | 0% | 0% | Low | MLP1
22 | F |  | Resolve Service case | Service | OOTB | [8 empty] | x |  | 50% | 50% | 0% | 0% | Low | MLP1
23 | F |  | Membership application | Membership application | Low | x |  | x | x | x | x | x | x |  |  | 75% | 25% | 0% | 0% | Medium | MLP2
24 | F |  | Membership renewal | Membership renewal | Medium | x |  | x | x | x | x | x | x |  |  | 25% | 50% | 50% | 0% | Medium | MLP2
25 | F |  | Exception path | Roadside assistance request | Low | [6 empty] | x | x |  |  | 25% | 50% | 50% | 0% | Low | MLP2
26 | F |  | Duplicate Case check | Roadside assistance request | OOTB | [10 empty] | 25% | 50% | 50% | 0% | Low | MLP2
Note on R2: Put an 'X' in the cell for any role/persona that applies to the corresponding Case Type or Feature
Note on Z2: For PL Set Business Value to Low, Medium, or High. This is another measure to help determine MLP
Note on AA2: Use this to prioritize items by release version with the product owners.

## Project Attributes
PROJECT ATTRIBUTES
ATTRIBUTE TYPE | ATTRIBUTE NAME | ATTRIBUTE VALUE | PROJECT ASSUMPTIONS
Platform / Application Info | Pega Version: | 8.8
| Application Name: | GoGoRoad
| Application Version: | 01.01
Co-Production | Staffing Model: | Co-Production
| Engagement Lead: | Pega Led / Client Co-Prod
Delivery | Delivery Methodology: | Agile/Scrum
| Scrum Maturity: | High
| Number of Scrum Teams | 3
Other Attributes | Pega Cloud or Existing On-Prem Instance: | Yes
| Data Import/Conversion Required: | None
| Localization (Enter # of additional languages): | 0
| Highly Regulated or Complex Company: | No
Special Packages in MLP1 | Robotics (10-week package implementation): | No
| Mktg & Dec Quick Win Package: | None
Risk | Other Contingencies (QA, Risk, etc.): | 0%
Note on B11: High - Client resources have extensive Scrum/Agile experience. Medium - Client resources have minimal Scrum/Agile experience. Low - Client resources have no Scrum/Agile experience.
Note on B12: 1 Scrum Team - 1 (L/S)BA - 1 LSA - 3 (S)SA (if Co-prod then 2 (S)SA ) - 2 Client resource testers - 0.5 UX/UI if co-prod - 1 Client BA - 2 Client SA EL/Scrum Master and Product Owner are automatically included where 1 EL and 1 PO can work with at most 2 scrum teams Robotics and Marketing/Decisioning resources added if needed.
Note on B14: Yes - You are using Pega Cloud or the client already has a Pega On-Prem server deployed and ready to go. Meaning that a new server does not need to be setup/deployed. No - Client will not be using Pega Cloud and needs to procure hardware and cycles to setup a server(s) for this application
Note on B15: Movement of live transactional data from one system to another
Note on B17: Select yes is your company is highly regulated, complex, has specific testing and validation requirements, or any other "special" project/process level methodology that would increase project timeline and scope of work.
Note on B19: Pega Robotics initial implementations are designed to take customers through a controlled enablement process which produces specific outcomes in a 10-12 week period. The journey includes: - Delivery of 1 - 3 high-value (medium complexity) automations - Ability to support in real world environment - Foundation to expand what was built - “Bucket” of post go-live support hours Team Includes: - EL - Engagement Leader (shared with PRPC project) - LRBA - Lead Robotics Business Architect (part time) - LRSA - Lead Robotics System Architect (part time) - (S)RSA - (Senior) Robotics System Architect (full time)
Note on B20: 10 week packages to build out one of the following: - Real-time cross-sell up-sell - Real time retension - Real time web personalization
Note on B22: Fudge Factor - 0%-100%
To be completed by the Consulting Team

## Reference Sizing
PARAMETERS FOR SIZING |  | ENGAGEMENT SCOPE |  | ESTIMATE RESULTS
|  | MLP Scope | Full Program | CATEGORY | SUB-CATEGORY |  | DETAIL
Process Complexity | Case Types & Features | 16 | 26 | Staffing Model | Co-Production | Pega | #REF!
| Average Complexity | Low | Low-Medium |  |  | Client (full time) | #REF!
| Personas | 4 | 4 | MLP1 First Release | MLP Duration |  | 4-6 weeks
(Based on staffing model above)
| Channels | 3 | 3 |  | MLP Total Hours |  | 5,000-7,090
Integration | New Interfaces | 0 | 3 |  | MLP Pega Hours |  | 2,300-3,300
| Existing Interfaces | 6 | 6 |  | MLP Client Hours |  | 2,700-3,790
Reports | Reports & Correspondences | 1 | 1 | Full Program (MLP1 & all future releases) | Full Program Duration |  | 4-7 weeks
(Based on staffing model above)
| Average Complexity | Low | Low-Medium |  | Total Hours |  | 5,600-9,500
Other Attributes | Special Project Attributes |  |  |  | Pega Hours |  | 2,600-4.400
[5 empty] | Client Hours |  | 3,000-5,100